## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Instructions
| Table 1 | Instructions
Instructions
| Table 1 | Instructions
Status
| Table 1 | Status

## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 35
PROJECT NAME | Subscription Model
PROJECT MENTOR (sponsor) | Amrutha Moorthy
TEAM MEMBERS | Pratham Omkar Pattanayak
Kotekal Methukula Santhosh
Kulkarni Aditya Shirish
Kalsariya Vikaskumar Manusukhbhai
Divya Prakash Yadav

## Status
Stripe Support | 35
Client | Subscription Model(SAAS)
Status tracker | Patenti Solutions
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Santhosh | 0.5 | 0.3 | Done |  | 0.2 | 66.6667
GIT Repository setup | Preparation | Pratham | 1 | 1.5 | Done |  | -0.5 | 33.3333
Client meeting | Coordination | Santhosh | 0.75 | 1 | Done | Make sure scoping questions are included | -0.25 | 25
Website Design Discussion | Preparation | All | 1.5 | 1 | Done |  | 0.5 | 50
Research existing technology | Preparation | All | 4 | 3 | Done |  | 1 | 33.3333
Project synopsis writeup | Documentation | Pratham + Santhosh | 2 | 3 | Done |  | -1 | 33.3333
Identify role owners | Preparation | All | 3 | 3 | Done | Multiple roles are OK - think about role & reponsibility distribution | 0 | 0
Team Meeting | Coordination | All | 0.5 | 0.5 | Done |  | 0 | 0
Status tracker | Documentation | Pratham+Aditya | 0.3 | 0.3 | Done |  | 0 | 0
Week 2 (January 22 - January 28)
Learn Django | Preparation | All | 8 | 9 | Done | Learn about Django framework | -1 | 11.1111
Stripe Support | Preparation | Pratham | 0.25 | 0.2 | Done | Check if the test mode is available for the project | 0.05 | 25
Client | Coordination | Pratham | 1 | 0.75 | Done |  | 0.25 | 33.3333
Status tracker | Documentation | Pratham + Aditya | 0.25 | 0.25 | Done |  | 0 | 0
Week 3 (January 29 - February 4)
SRS document | Requirements | Santhosh + Pratham | 3 | 4 | Done |  | -1 | 25
Interface study | Design | All | 4 | 4 | Done | Study about handshake mechanism | 0 | 0
Contact other gateways | Requirements | All | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Pratham + Aditya | 0.25 | 0.25 | Done |  | 0 | 0
Week 4 (February 12-February 18)
SRS document (modified) | Documentation | Santhosh + Pratham | 2 | 3 | Done |  | -1 | 33.3333
Client meeting | Coordination | Pratham | 0.25 | 0.5 | Done |  | -0.25 | 50
Database Design | Design | Santhosh + Pratham | 1 | 1.25 | Done |  | -0.25 | 20
Database creation | Development | Santhosh | 3 | 4 | Done |  | -1 | 25
User Authentication | Development | Pratham | 2 | 3 | Done |  | -1 | 33.3333
Module modification | Design | Santhosh+Pratham | 1 | 1 | Done |  | 0 | 0
Module allocation | Coordination | All | 1 | 1 | Done |  | 0 | 0
Week 5(February 19 - February 25)
Plans web page | Development | Vikas | 2 | 3 | Done | Make plans web page using html+css+bootstrap | -1 | 33.3333
Django set up for Plans, details and payment pages | Development | Aditya | 1.5 | 2 | Done | Basic setup of 3 web pages together in Django for Plans, details and payment pages | -0.5 | 25
Test Plan Tracker | Documentation | Aditya + Pratham | 0.5 | 0.5 | Done |  | 0 | 0
Plan details and payment web page | Development | Aditya + Vikas | 5 | 5.5 | Done |  | -0.5 | 9.0909
Week 6(February 26 - March 3)
User authentication | Development | Santhosh+Pratham | 2 | 3 | Done | Make login web page using html+css+bootstrap | -1 | 33.3333
Session management | Development | Santhosh+Pratham | 4 | 4 | Done | Manage backend for user authentication by session tracking | 0 | 0
Database management | Development | Santhosh+Pratham | 3 | 4 | Done |  | -1 | 25
User profile and FAQ page | Development | Divya | 4 |  | Done | Make Profile and FAQ web pages using html+css+bootstrap
Week 7(March 4 - March 10)
Integration(Except gateway) | Development | Santhosh | 6 | 5 | Done | The modules are successfully integrated | 1 | 20
Checkout Page | Development | Vikas + Aditya | 3 | 3 | Done |  | 0 | 0
Razorpay Development | Development | Pratham | 2 | 3 | Done |  | -1 | 33.3333
Week 8(March 11 - March 17)
Razorpay Integration | Development | Santhosh+Pratham | 3 | 3 | Done |  | 0 | 0
CSS modification | Development | Aditya + Vikas | 2.5 | 3 | Done |  | -0.5 | 16.6667
Release 1 coding | Development | All | 6 | 6 | Done |  | 0 | 0
Check for all pre-decided test cases for R1 | Testing | Santhosh+Pratham | 2 | 2 | Done |  | 0 | 0
Week 9(March 18 - March 24)
Release 1 presentation | Delivery | All | 1 | 1 | Done |  | 0 | 0
R2 plan | Development | All | 1 |  | Planned
Week 10(March 25 - March 31)
Meet with sir for new project | Coordination | All | 0.5 | 0.5 | Done |  | 0 | 0
Research about Conference Registration Management System | Preparation | All | 2.5 | 3 | Done |  | -0.5 | 16.6667
Week 11(April 1 - April 7)
Understanding and discussion on low code platform for CRMS | Preparation | All | 2 | 2 | Done |  | 0 | 0
Research existing technology | Preparation | All | 2 | 2 | Done |  | 0 | 0
SRS document | Requirements | All | 3 | 3 | Done |  | 0 | 0